## Work Log
WORK LOG FOR THE PROJECT
NAME | CONTACT
Lan Dinh | 672-866-0515
DEPARTMENT | SUPERVISOR |  |  |  | TOTAL TIME ON SCHEDULE
Complete non-shaded cells only. Shaded cells populate automatically.
ACTIVITY | DATE | START TIME | END TIME | TOTAL TIME | STATUS | NOTES
Doing Interest and Expertise Survey to find out what skills and technologies want to work on | 2025-01-12 | 17:00 | 18:00 | 1:00 | Complete | Survey completed successfully. Identified interest in Mobile Developments and Building Dashboards by Tableau and PowerBI
Finding the topic for the research project, looking for paper researches and previous works | 2025-01-14 | 17:00 | 19:00 | 2:00 | Complete | Explored multiple topics. Narrowed down to Activity Reminder Mobile App.
Creating and adding the Client in the Repo | 2025-02-01 | 9:00 | 9:00 | 0:00 | Complete | Client added to the repository. No time spent as it was instantaneous.
Writing the draft proposal for the Client | 2025-01-20 | 9:00 | 15:00 | 6:00 | Complete
Discussing to the Client about the choosing topic is Activity Reminder Mobile App for Douglas College students | 2025-01-23 | 10:00 | 10:30 | 0:30 | Complete | Client provided feedback. Topic was approved initially but later changed.
Changing the topic to the Dashboard Development by Python for analyzing movie trends and insights | 2025-01-24 | 10:00 | 10:30 | 0:30 | Approved | Topic changed based on client's suggestion. New focus on Python dashboard developments.
Rewriting the proposal | 2025-01-24 | 13:00 | 20:00 | 7:00 | Complete | Proposal rewritten to reflect the new topic. Submitted for approval. And it was approved
Cleaning database (Netflix database) by using JupyterNotebook | 2025-01-26 | 13:00 | 15:00 | 2:00 | Complete | Data cleaned and prepared for analysis.
Writing the Progress Report | 2025-01-29 | 17:00 | 22:00 | 5:00 | Complete
Writing questions for an interview | 2025-02-01 | 16:00 | 17:00 | 1:00 | Complete | Questions are being developed for Participant A and B.
Drafting the ideas for the dashboard | 2025-02-02 | 17:00 | 18:00 | 1:00 | Complete | Initial ideas for dashboard layout and functionality drafted.
Coding for the dashboard by Python | 2025-02-06 | 13:00 | 23:00 | 10:00 | In Progress | Coding in progress. Focused on data visualization and user interface.
Doing the interview with Participant A | 2025-02-08 | 14:00 | 14:30 | 0:30 | Complete | Still finding the potential participant and scheduling. The deadline is Feb 10
Doing the interview with Participant B | 2025-02-10 | 9:00 | 9:30 | 0:30 | Complete | Still finding the potential participant and scheduling. The deadline is Feb 12
Analyzing interview results | 2025-02-14 | 17:00 | 19:00 | 2:00 | Complete | Analyze feedback from Participants A and B to refine dashboard features.
Writing the Interview Questions and Reponses | 2025-02-14 | 19:00 | 21:00 | 2:00 | Complete | Interview questions and responses documented and uploaded to GitHub.
Cleaning database (IMDB database) by using JupyterNotebook | 2025-02-16 | 15:00 | 16:00 | 1:00 | Complete | Data cleaned and prepared for analysis.
Adding IMDb dataset (imdb_top_1000.csv) to the repository | February 16, 2025 | 12:00 | 12:00 | 0:00 | In Progress | Primary dataset for “Gross Earnings Explorer” added to repo. No time spent as it was instantaneous.
Coding the “Movie Trends Dashboard” welcome page | February 18, 2025 | 12:00 | 13:00 | 1:00 | Complete | Initial script (Welcome.py) completed with layout and styling
Coding the “Explore Global Trends” dashboard | 2025-02-20 | 15:00 | 20:00 | 5:00 | Complete | Initial script (GlobalTrend.py) completed with Netflix-based visualizations and filters. Enhanced with custom styling.
Drafting the midterm report | 2025-02-24 | 9:30 | 10:30 | 1:00 | Complete | Midterm report drafted to summarise progress, including interviews, and initial coding efforts.
Coding the “Gross Earnings Explorer” dashboard | 2025-03-01 | 9:00 | 16:00 | 7:00 | Complete | Initial script (GrossEarnings.py) completed with data loading, cleaning, and filters.
Enhancing dashboards with custom styling and informative elements | 2025-03-05 | 12:00 | 20:00 | 8:00 | Complete | Improved visual appeal and usability of Welcome page, Explore Global Trends, and Gross Earnings Explorer dashboards.
Drafting the progress report #2 | 2025-03-09 | 15:00 | 19:00 | 4:00 | Complete | Progress report #2 drafted to detail dashboard development, interview insights, and visualization progress.
Creating user authentication for the dashboards | 2025-03-14 |  |  | 0:00 | In Progress | Began implementing user authentication for dashboards to enhance security and personalization
Creating history watchlist for each user |  |  |  | 0:00 | In Progress

## Dropdown Keys
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold
Other 1
Other 2