## Work Log
WORK LOG FOR THE PROJECT
NAME | CONTACT
Lan Dinh | 672-866-0515
DEPARTMENT | SUPERVISOR |  |  |  | TOTAL TIME ON SCHEDULE
Complete non-shaded cells only. Shaded cells populate automatically.
ACTIVITY | DATE | START TIME | END TIME | TOTAL TIME | STATUS | NOTES
Doing Interest and Expertise Survey to find out what skills and technologies want to work on | 2025-01-12 | 17:00 | 18:00 | 1:00 | Complete | Survey completed successfully. Identified interest in Mobile Developments and Building Dashboards by Tableau and PowerBI
Finding the topic for the research project, looking for paper researches and previous works | 2025-01-14 | 17:00 | 19:00 | 2:00 | Complete | Explored multiple topics. Narrowed down to Activity Reminder Mobile App.
Creating and adding the Client in the Repo | 2025-02-01 | 9:00 | 9:00 | 0:00 | Complete | Client added to the repository. No time spent as it was instantaneous.
Writing the draft proposal for the Client | 2025-01-20 | 9:00 | 15:00 | 6:00 | Complete
Discussing to the Client about the choosing topic is Activity Reminder Mobile App for Douglas College students | 2025-01-23 | 10:00 | 10:30 | 0:30 | Complete | Client provided feedback. Topic was approved initially but later changed.
Changing the topic to the Dashboard Development by Python for analyzing movie trends and insights | 2025-01-24 | 10:00 | 10:30 | 0:30 | Approved | Topic changed based on client's suggestion. New focus on Python dashboard developments.
Rewriting the proposal | 2025-01-24 | 13:00 | 20:00 | 7:00 | Complete | Proposal rewritten to reflect the new topic. Submitted for approval. And it was approved
Cleaning database (Netflix database) by using JupyterNotebook | 2025-01-26 | 13:00 | 15:00 | 2:00 | Complete | Data cleaned and prepared for analysis.
Writing the Progress Report | 2025-01-29 | 17:00 | 22:00 | 5:00 | Complete
Writing questions for an interview | 2025-02-01 | 16:00 | 17:00 | 1:00 | Complete | Questions are being developed for Participant A and B.
Drafting the ideas for the dashboard | 2025-02-02 | 17:00 | 18:00 | 1:00 | Complete | Initial ideas for dashboard layout and functionality drafted.
Coding for the dashboard by Python | 2025-02-06 | 13:00 | 23:00 | 10:00 | In Progress | Coding in progress. Focused on data visualization and user interface.
Doing the interview with Participant A | 2025-02-08 | 14:00 | 14:30 | 0:30 | Complete | Still finding the potential participant and scheduling. The deadline is Feb 10
Doing the interview with Participant B | 2025-02-10 | 9:00 | 9:30 | 0:30 | Complete | Still finding the potential participant and scheduling. The deadline is Feb 12
Analyzing interview results | 2025-02-14 | 17:00 | 19:00 | 2:00 | Complete | Analyze feedback from Participants A and B to refine dashboard features.
Writing the Interview Questions and Reponses | 2025-02-14 | 19:00 | 21:00 | 2:00 | Complete | Interview questions and responses documented and uploaded to GitHub.
Cleaning database (IMDB database) by using JupyterNotebook | 2025-02-16 | 15:00 | 16:00 | 1:00 | Complete | Data cleaned and prepared for analysis.
Adding IMDb dataset (imdb_top_1000.csv) to the repository | February 16, 2025 | 12:00 | 12:00 | 0:00 | In Progress | Primary dataset for “Gross Earnings Explorer” added to repo. No time spent as it was instantaneous.
Coding the “Movie Trends Dashboard” welcome page | February 18, 2025 | 12:00 | 13:00 | 1:00 | Complete | Initial script (Welcome.py) completed with layout and styling
Coding the “Explore Global Trends” dashboard | 2025-02-20 | 15:00 | 20:00 | 5:00 | Complete | Initial script (GlobalTrend.py) completed with Netflix-based visualizations and filters. Enhanced with custom styling.
Drafting the midterm report | 2025-02-24 | 9:30 | 10:30 | 1:00 | Complete | Midterm report drafted to summarise progress, including interviews, and initial coding efforts.
Coding the “Gross Earnings Explorer” dashboard | 2025-03-01 | 9:00 | 16:00 | 7:00 | Complete | Initial script (GrossEarnings.py) completed with data loading, cleaning, and filters.
Enhancing dashboards with custom styling and informative elements | 2025-03-05 | 12:00 | 20:00 | 8:00 | Complete | Improved visual appeal and usability of Welcome page, Explore Global Trends, and Gross Earnings Explorer dashboards.
Drafting the progress report #2 | 2025-03-09 | 15:00 | 19:00 | 4:00 | Complete | Progress report #2 drafted to detail dashboard development, interview insights, and visualization progress.
Creating user authentication for the dashboards | 2025-03-14 | 19:00 | 21:30 | 2:30 | Complete | Built the login system and a registration feature to Welcome.py. Included checks to prevent duplicate usernames and securely appended new users’ data to users.json
Adding profile editing functionality | 2025-03-18 | 11:15 | 17:00 | 5:45 | Complete | Implemented an edit form on the profile page to update full name, date of birth, email, and password. Added validation for password confirmation and updated users.json with changes.
Intergrating avatar upload feature | 2025-03-19 | 19:00 | 19:30 | 0:30 | Complete | Added avatar upload supports to the profile page.
Creating the movie checklist with search suggestions and pagination | 2025-03-22 | 17:30 | 22:30 | 5:00 | Complete | Added keyword suggestions and pagination (Previous/Next) to the Discover Movies tab for better usability.
Drafting the progress report #3 | 2025-03-23 | 7:00 | 7:45 | 0:45 | Complete | Wrote Progress Report #3 to detail this week’s work: user authentication, profile page, and movie checklist features.
Implementing watchlist and history tabs with interactive features | 2025-03-26 | 12:00 | 16:15 | 4:15 | Complete | Added functionality to mark movies as watched, remove them, and display watched movies with timestamps in separate tabs.
Drafting Adding user rating system with emojisthe progress report #4 | 2025-03-27 | 21:00 | 22:15 | 1:15 | Complete | Integrated an emoji-based rating system (1–9) for watched movies in the History tab.
Creating notification system | 2025-03-29 | 21:00 | 22:45 | 1:45 | Complete | Built a notification popover with unread/read styling, plus options to mark all as read or clear notifications
Drafting the progress report #4 | 2025-03-30 | 22:00 | 22:30 | 0:30 | Complete | Wrote Progress Report #4 to summarize this week’s enhancements to the movie checklist feature.
0:00
0:00
0:00
0:00

## Dropdown Keys
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold
Other 1
Other 2